## TERM
PRODUCT BACKLOG
YEAR
| ID | ITEM | OWNER | PRIORITY | EFFORT | STATUS | DEFINITION OF DONE | NOTES
| 1 | View Menu | Matthies Abera | 1 | 17 | Included in spint 1 | Given that I am on the Menu View, When I click on the View Menu button, Then I am Presented With a Menu View
| 2 | Add Menu Item | Matthies Abera | 2 | 11 | Included in spint 2 | Given that I am on the Menu View, When I click on the Add Menu Item button, Then a form view is shown so that I can add a new menu item
| 3 | Edit Menu Item | Matthies Abera | 3 | 10 | Included in spint 3 | Given that I am on the Menu View, When I clcik on the Edit Menu Item button, Then a form view is shown so that I can edit a current menu item
| 4 | Delete Menu Item | Matthies Abera | 4 | 9 | Included in spint 4 | Given that I am on the Menu View, When I click on the Delete Menu Item button, Then a form view is shown so that I can delete a current menu item
| 5 | Look At Current Tables Seated | Matthies Abera | 5 | 3 | On Product Backlog | Given that I am on the Order View, When I stay on the order view, Then all tables presently open are tinted
| 6 | Take An Order For A Table | Matthies Abera | 6 | 12 | On Product Backlog | Given that I am on the Order View, When I click on a table, Then the view changes to the docket view and I can start the order
| 7 | Edit An Order | Matthies Abera | 7 | 4 | On Product Backlog | Given that I am on the Order View, When I click on a table, Then the view changes to the docket view and I can edit the order
| 8 | Delete An Order | Matthies Abera | 8 | 2 | On Product Backlog | Given that I am on the docket view, When I click the delete button, Then the order is deleted
| 9 | Pay And Close A Table | Matthies Abera | 9 | 8 | On Product Backlog | Given that I am on the docket view, When I click the close table button, Then the table is closed and I am sent to the tables view
| 10 | View Revenue For The Day | Matthies Abera | 10 | 3 | On Product Backlog | Given that I am on the application, When I look in the top right corner, Then I can see the daily revenue amount
| 11 | View Most Popular Items | Matthies Abera | 11 | 12 | On Product Backlog | Given that I am on the index view, Whck I click on the Analytics View Button, Then the Analytics View is shown the business insights
| 12 | View "To (Period)" Business Analytics | Matthies Abera | 12 | 20 | On Product Backlog | Given that I am on the index view, When I click on the Analytics View button, Then the Analytics View is shown with business insights

## CREDITS
COLLEGE
CREDIT PLANNER
YEAR
Degree Title
OVERALL PROGRESS |  | OVERALL PROGRESS
3.5 | 3.50 Current GPA | 0.66667 | 67% Completed
Note: The following credit summary is automatically populated by your entries in the College Courses table below
REQUIREMENT | TOTAL CREDITS | EARNED | NEEDED
Academic Major | 4 | 4 | 0
Academic Minor | 3 | 0 | 3
Elective Course | 2 | 2 | 0
General Study | 0 | 0 | 0
TOTAL | 9 | 6 | 3
College Courses
COURSE TITLE | COURSE # | REQUIREMENT | CREDITS | COMPLETED | GRADE | TERM
[Course 1] | [Number] | Academic Major | 4 | Yes | 4 | Term 1
[Course 2] | [Number] | Academic Minor | 3 | No |  | Term 1
[Course 3] | [Number] | Elective Course | 2 | Yes | 3 | Term 1

## BUDGET
COLLEGE
BUDGET TRACKER
YEAR
My Budget
PERCENTAGE OF INCOME SPENT
74.55%
74.55%
NET MONTHLY INCOME |  | NET MONTHLY EXPENSES |  | BALANCE
2750 |  | 2050 |  | 700
[5 empty] | Months in term | 4
MONTHLY INCOME | 2750 | MONTHLY EXPENSES | 1675 | TERM EXPENSES | 1500 | 375
ITEM | AMOUNT | ITEM | AMOUNT | ITEM | AMOUNT | PER MONTH
Fixed income | 1500 | Rent | 300 | Tuition | 750 | 187.5
Financial aid | 500 | Utilities | 50 | Lab fees | 250 | 62.5
Loans | 500 | Cell phone | 75 | Books | 500 | 125
Other income | 250 | Groceries | 250 | Deposits | 0 | 0
|  | Auto expenses | 50 | Transportation | 0 | 0
|  | Student loans | 500 | Other fees | 0 | 0
|  | Credit cards | 275
|  | Insurance | 125
|  | Entertainment | 50
|  | Miscellaneous | 0

## BOOKS
COLLEGE
BOOK TRACKER
YEAR
Book List
TITLE | AUTHOR | COURSE | WHERE TO BUY? | ISBN | NOTES
[Book Title] | [Author] | [Course] | [Location] | [Number]
[Book Title] | [Author] | [Course] | [Location] | [Number]
[Book Title] | [Author] | [Course] | [Location] | [Number]