## TERM
PRODUCT BACKLOG
YEAR
| PBI ID | PBI NAME | TASK ID | TASK | ASSIGNED TO | NOT STARTED | IN PRGROGRESS | COMPLETED | NOTES (ESTIMATE, TIME SPENT)
| 1 | View Menu | 1.1 | Create all the Menu Model Data | Matthies Abera |  |  | X | Estimate hours: 3, Actual hours: 3
|  |  | 1.2 | Create Menu Buton and Subsequent View | Matthies Abera |  |  | X | Estimate hours: 1, Actual hours: 1
|  |  | 1.3 | Create View Menu Button and Subsequent View | Matthies Abera |  |  | X | Estimate hours: 3, Actual hours: 2
|  |  | 1.4 | Create Pop Up with Name, Description and Price when Item is clicked or held down | Matthies Abera |  |  | X | Estimate hours: 6, Actual hours: 2
|  |  | 1.5 | Testing | Matthies Abera |  | X |  | Estimate hours: 0, Actual hours: 0
| 2 | Add Menu Item | 2.1 | Create Add Menu Item Button | Matthies Abera |  |  | X | Estimate hours: 1, Actual hours: 1
|  |  | 2.2 | Create Form View for New Menu Item | Matthies Abera |  |  | X | Estimate hours: 3, Actual hours: 3
|  |  | 2.3 | Create Function to Add to Menu | Matthies Abera |  |  | X | Estimate hours: 2, Actual hours: 4
|  |  | 2.4 | Try/Catch Verification for incorrect input with notification message if error | Matthies Abera |  |  | X | Estimate hours: 3, Actual hours: 1
|  |  | 2.5 | Testing | Matthies Abera |  | X |  | Estimate hours: 0, Actual hours: 0
| 3 | Edit Menu Item | 3.1 | Create Edit Menu Item Button | Matthies Abera |  |  | X | Estimate hours: 1, Actual hours: 1
|  |  | 3.2 | Create Form View for Editing a current Menu Item | Matthies Abera |  |  | X | Estimate hours: 2, Actual hours: 4
|  |  | 3.3 | Create Function to Edit Menu Item | Matthies Abera |  |  | X | Estimate hours: 2, Actual hours: 1
|  |  | 3.4 | Try/Catch Verification for incorrect input with notification message if error | Matthies Abera |  |  | X | Estimate hours: 2, Actual hours: 1
|  |  | 3.5 | Testing | Matthies Abera |  | X |  | Estimate hours: 0, Actual hours: 0
| 4 | Delete Menu Item | 4.1 | Create Delete Menu Item Button | Matthies Abera |  |  | X | Estimate hours: 1, Actual hours: 1
|  |  | 4.2 | Create From View for Deleting a Menu Item | Matthies Abera |  |  | X | Estimate hours: 3, Actual hours: 1
|  |  | 4.3 | Create Function to Delete from Menu | Matthies Abera |  |  | X | Estimate hours: 3, Actual hours: 1
|  |  | 4.4 | Testing | Matthies Abera |  | X |  | Estimate hours: 2, Actual hours: 1

## CREDITS
COLLEGE
CREDIT PLANNER
YEAR
Degree Title
OVERALL PROGRESS |  | OVERALL PROGRESS
3.5 | 3.50 Current GPA | 0.66667 | 67% Completed
Note: The following credit summary is automatically populated by your entries in the College Courses table below
REQUIREMENT | TOTAL CREDITS | EARNED | NEEDED
Academic Major | 4 | 4 | 0
Academic Minor | 3 | 0 | 3
Elective Course | 2 | 2 | 0
General Study | 0 | 0 | 0
TOTAL | 9 | 6 | 3
College Courses
COURSE TITLE | COURSE # | REQUIREMENT | CREDITS | COMPLETED | GRADE | TERM
[Course 1] | [Number] | Academic Major | 4 | Yes | 4 | Term 1
[Course 2] | [Number] | Academic Minor | 3 | No |  | Term 1
[Course 3] | [Number] | Elective Course | 2 | Yes | 3 | Term 1

## BUDGET
COLLEGE
BUDGET TRACKER
YEAR
My Budget
PERCENTAGE OF INCOME SPENT
74.55%
74.55%
NET MONTHLY INCOME |  | NET MONTHLY EXPENSES |  | BALANCE
2750 |  | 2050 |  | 700
[5 empty] | Months in term | 4
MONTHLY INCOME | 2750 | MONTHLY EXPENSES | 1675 | TERM EXPENSES | 1500 | 375
ITEM | AMOUNT | ITEM | AMOUNT | ITEM | AMOUNT | PER MONTH
Fixed income | 1500 | Rent | 300 | Tuition | 750 | 187.5
Financial aid | 500 | Utilities | 50 | Lab fees | 250 | 62.5
Loans | 500 | Cell phone | 75 | Books | 500 | 125
Other income | 250 | Groceries | 250 | Deposits | 0 | 0
|  | Auto expenses | 50 | Transportation | 0 | 0
|  | Student loans | 500 | Other fees | 0 | 0
|  | Credit cards | 275
|  | Insurance | 125
|  | Entertainment | 50
|  | Miscellaneous | 0

## BOOKS
COLLEGE
BOOK TRACKER
YEAR
Book List
TITLE | AUTHOR | COURSE | WHERE TO BUY? | ISBN | NOTES
[Book Title] | [Author] | [Course] | [Location] | [Number]
[Book Title] | [Author] | [Course] | [Location] | [Number]
[Book Title] | [Author] | [Course] | [Location] | [Number]